## Sprints Schedule
Sprints/Release Schedule
End of sprint activities
Release # | Sprint # | Start | End | Stand Up Meeting | Demo | Retrospective | Sprint Planning | Due at the end of the sprint
| 1 | 2018-02-21 | 2018-02-27 |  |  |  |  | Sprint 1 Report
| 2 | 2018-02-28 | 2018-03-06 |  |  |  |  | Sprint 2 Report
Release 1 | 3 | 2018-03-07 | 2018-03-13 |  |  |  |  | Sprint 3 Report, R1 Code, Release 2 plan, Sprint 4 Plan
| 4 | 2018-03-14 | 2018-03-20 |  |  |  |  | Sprint 4 Report
| 5 | 2018-03-21 | 2018-03-27 |  |  |  |  | Sprint 5 Report
Release 2 | 6 | 2018-03-28 | 2018-04-03 |  |  |  |  | Sprint 6 Report, R2 Code, Release 3 plan, Sprint 7 Plan
| 7 | 2018-04-04 | 2018-04-10 |  |  |  |  | Sprint 7 Report
| 8 | 2018-04-11 | 2018-04-17 |  |  |  |  | Sprint 8 Report
Release 3 | 9 | 2018-04-18 | 2018-04-24 |  |  |  |  | Sprint 9 Report, R3 Code